## Slide 1: The London Ambulance fiasco
The London Ambulance Service (LAS) Computer Aided Despatch (CAD) system failed dramatically on October 26th 1992 shortly after it was introduced:
  The system could not cope with the load placed on it by normal use;
  The response to emergency calls was several hours;
  Ambulance communications failed and ambulances were lost from the system.
A series of errors were made in the procurement, design, implementation, and introduction of the system.

## Slide 2: London Ambulance Service
Managed by South West Thames Regional Health Authority.
Largest ambulance service in the world (LAS inquiry report)
  Covers geographical area of over 600 square miles
  Resident population of 6.8 million people (greater during daytime, especially central London);
  Carries over 5,000 patients every day;
  2,000-2,500 calls received daily, of which 1,300-1,600 are emergency calls.

## Slide 3: Computer-aided despatch systems
Provide one or more of the following:
  Call taking;
  Resource identification;
  Resource mobilisation;
  Ambulance resource management.
Consist of:
  CAD software & hardware;
  Gazetteer and mapping software;
  Communications interface (RIFS).
  Radio system;
  Mobile data terminals (MDTs);
  Automatic vehicle location system (AVLS).

## Slide 4: The manual system to be replaced
Call taking
  Recorded on form; location identified in map book; forms sent to central collection point on conveyor belt;
Resource identification
  Form collected; passed onto resource allocator depending on region; duplicates identified. Resource allocator decides on which resource to be mobilised; recorded on form and passed to dispatcher;
Resource mobilisation
  Dispatcher telephones relevant ambulance station, or passes mobilisation instructions to radio operator if ambulance already on road;
Whole process meant to take < 3 minutes.

## Slide 5: Concept/design of the CAD system
Existing systems dismissed as inadequate and impossible to modify to meet LAS’s needs
  Intended functionality “greater than available from any existing system”.
Desired system:
  To consist of Computer Aided Dispatch; Computer map display; Automatic Vehicle Location System (AVLS);
  Must integrate with existing MDTs and RIFS (Radio Interface System).
Success dependent upon:
  Near 100% accuracy and reliability of technology;
  Absolute cooperation from all parties including CAC staff and ambulance crews.

## Slide 6: Problems: Procurement (i)
Contract had to be put out to open tender
  Regulations emphasis is on best price;
  35 companies expressed interest in providing all or part of the system
    Most raised concerns over the proposed timetable of less than 1 year until full implementation.
Previous Arthur Andersen report largely ignored
  Recommended budget of £1.5M and 19 month timetable for packaged solution. Both estimates to be significantly increased if packaged solution not available;
  Report never shown to new Director of Support Services.
Only 1 out of 17 proposals met all of the project team’s requirements, including budget of £1.5M.

## Slide 7: Problems: Procurement (ii)
Successful consortium
  Apricot, Systems Options (SO), Datatrak; bid at £937k was £700k cheaper than the nearest bid;
  SO’s quote for the CAD development was only £35k
    Their previous development experience for the emergency services was only for administrative systems.
  Ambiguity over lead contractor.
2 key members of evaluation team:
  Systems manager: Career ambulance man, not an IT professional, already told that he was to make way for a properly qualified systems manager;
  Analyst: Contractor with 5 years experience working with LAS.

## Slide 8: Problems: Project management
Lead contractor responsible
  Meant to be SO, but they quickly became snowed under, so LAS became more responsible by default;
  No relevant experience at LAS or SO.
Concerns raised at project meeting not followed-up.
SO regularly late in delivering software
  Often also of suspect quality, with software changes put through ‘on the fly’.
Formal, independent QA did not exist at any stage throughout the CAD system development.
Meanwhile, various technical components of the system are failing regularly, and deadlines missed.

## Slide 9: Problems: Human resources & training (i)
Generally positive attitude to the introduction of new technology.
Ambiguity over consultation of ambulance crews for development of original requirements.
Circumstantial evidence of resistance by crews to Datatrak equipment, and deliberate misleading of the system.
Large gap between when crews and CAC staff were trained and implementation of the system.
Inability of the CAC and ambulance staff to appreciate each others’ role
  Exacerbated by separate training sessions.

## Slide 10: Problems: Human resources & training (ii)
Poor industrial relations.
Management ‘fear of failure’.
CAD system seen as solution to management’s desire to reduce ‘outdated’ working practices.
System allocated nearest resource, regardless of originating station.
System removed flexibility in resource allocation.
Lack of voice contact exacerbated “them and us”.
Technical problems reduced confidence in the system for ambulance crews and CAC staff.

## Slide 11: System problems
Need for near perfect information
  Without accurate knowledge of vehicle locations and status, the system could not allocate optimum resources.
Poor interface between crews, MDTs & the system
  There were numerous possible reasons for incorrect information being passed back to the system.
Unreliability, slowness and operator interface
  Numerous technical problems with the system, including:
    Failure to identify all duplicated calls;
    Lack of prioritisation of exception messages;
    Exception messages and awaiting attention queues scroll off top of screen.

## Slide 12: Configuration changes
Implementation of the system on 26 October involved a number of significant changes to CAC operation, in particular:
  Re-configuring the control room;
  Installing more CAD terminals and RIFS screens;
  No paper backup system;
  Physically separating resource allocators from radio operators and exception rectifiers;
  Going ‘pan London’ rather than operating in 3 divisions;
  Using only the system proposed resource allocations;
  Allowing some call takers to allocate resources;
  Separate allocators for different call sources.

## Slide 13: So, what happened?
Changes to CAC operation made it extremely difficult for staff to intervene and correct the system.
As a consequence, the system rapidly knew the correct location and status of fewer and fewer vehicles, leading to:
  Poor, duplicated and delayed allocations;
  A build up of exception messages and the awaiting attention list;
  A slow up of the system as the messages and lists built up;
  An increased number of call backs and hence delays in telephone answering.

## Slide 14: Why did it fail?
Technically, the system did not fail on October 26th
  Response times did become unacceptable, but overall the system did what it had been designed to do!
  Failed 3 weeks later due to a program error - this was a memory leak where allocated memory was not completely released.
It depends who you ask!
  Management;
  Union;
  System manager;
  Government.

## Slide 15: Lessons learned
Inquiry report makes detailed recommendations for future development of the LAS CAD system, including:
  Focus on repairing reputation of CAD within the service;
  Increasing sense of ‘ownership’ for all stakeholders;
  They still believe that a technological solution is required;
  Development process must allow fully for consultation, quality assurance, testing, training;
  Management and staff must have total, demonstrable, confidence in the reliability of the system;
  Any new system should be introduced in a stepwise approach.